{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["平安城市电子围栏建设项目"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"平安城市电子围栏建设项目","index":0,"n_rows":26,"n_cols":9,"rows_kept":26,"merged":[[0,0,0,8],[2,1,2,8],[3,1,3,2],[3,4,3,6],[4,1,4,8],[5,1,5,8],[6,1,6,8],[7,0,7,2],[7,3,7,8],[8,0,8,8],[9,0,11,0],[9,6,9,8],[10,6,11,8],[12,0,12,8],[13,6,13,7],[14,0,19,0],[14,1,14,4],[14,6,14,7],[15,1,16,1],[15,6,15,7],[16,6,16,7],[17,1,18,1],[17,6,17,7],[19,6,19,7],[20,0,23,0],[20,1,22,1],[20,6,20,7],[23,6,23,7],[24,0,24,4],[25,0,25,8]],"flags":["formulas_cached_only"]}
["咸宁市财政项目支出绩效自评表\n（2019年度）"]
["填报单位（盖章）：咸宁市公安局温泉分局"]
["项目名称","平安城市电子围栏建设项目"]
["主管部门","咸宁市公安局温泉分局",null,"项目实施单位","咸宁市公安局温泉分局",null,null,"项目绩效责任人","蔡振雄"]
["项目属性","1、部门项目   √      2、二次审批项目   □  3、上级转移支付项目   □   2、调整预算追加项目   □"]
["项目种类","1、专项业务类  √        2、公共服务类   □   3、能力建设类 □    4、经济发展类 □"]
["项目类型","1、经常性项目   √        2、跨年一次性项目 □      3、当年一次性项目   □"]
["年度绩效目标完成情况",null,null,"　　根据治安部门机构设置人员及业务配置，结合近三年治安经费平均经费支出测算。弥补公用经费的不足,对治安管理提供基本经费保障，更好完成各类治安管理工作任务。改善社会治安环境，保障人民群众安居乐业 。 "]
["预算执行情况评价"]
["项目预算执行情况\n（20分）","项目当年预算","预算数","全年执行数","执行率","自评分","预决算偏离原因分析"]
[null,"年度资金总额：",205.2,102.41,{"v":0.49907407407407406,"d":"49.91%"},5,"　　　我局2018年度采购的是2G热点采集设备，已经不能适应当前公安工作。如果继续采购2G热点采集设备，将面临刚安装不久就要淘汰的风险。为了节约经费，更好的向科技要警力，并与市局设备配套我局决定在2020年采购最新型的5G热点采集设备，导致2019年度执行率低。"]
[null,"其中：当年一般公共预算拨款",205.2,102.41,{"v":0.49907407407407406,"d":"49.91%"},5]
["绩效目标完成情况评价"]
["一级指标","二级指标","三级指标","年初目标值","实际完成值 ","自评分","未完成原因分析与改进措施",null,"绩效指标分析与建议"]
["产出指标（40分）","合计",{"$nulls":3},50]
[null,"数量指标","覆盖率、数据采集准确率",{"v":1,"d":"100%"},"效果显著",5]
[null,null,"设备数量","分局辖区内分布10个安装点","效果显著",5]
[null,"质量指标","合同执行","按合同内容执行到位","效果显著",5]
[null,null,"验收达标","按合同质量及技术要求，采购设备达标","效果显著",6]
[null,"时效指标","完成及时率",{"v":1,"d":"100%"},"按时完成",5]
["效果指标（40分）","社会效益指标","队伍建设","实现公安机关队伍业务精准化","效果显著",6]
[null,null,"落实党和政府政策","贯彻落实公安部门的基本职能","效果显著",6]
[null,null,"维护社会和谐稳定","提高公安机关战斗力，从而犯罪率下降","效果显著",6]
[null,"服务对象满意度指标","公众满意度",{"v":1,"d":"100%"},{"v":1,"d":"100%"},6]
["总计",{"$nulls":4},60]
["备注：\n1.年度资金总额＝一般公共预算拨款+政府性基金预算财政拨款+上年度财政拨款结余。\n2.“绩效指标分析”是指参考历史数据、行业标准及绩效目标实际完成情况等相关资料，从“是否与项目密切相关，指标值是否可获取，指标值设置是否合理”等角度，找出需要改进的指标，并逐项提出次年的编制意见和建议。"]